## R1001-Data
R1001 - Dataset
Dataset name/identifier | Owned/To be acquired/To be generated | Is data set Synthetic? | For each class, # of images in dataset | Pixel Dimensions per class in each dataset | # of images in dataset targeted | Cost of each dataset | Explanation & Comments, including assumptions | Amount of work (Human * Week): Generate Data | Amount of work (Human * Week): Pre-process | Amount of work (Human * Week): Labeling | Aitronx's Internal Cost
OD - Human (Color of clothing) |  |  | 30K | 130x400
OD - Human (Holding a bag) | [6 empty] | EfficeintDet can detect backbag/handbag
OD - Human (wearing a hard hat) |  | N | 28K | 50x35
OD - Human (wearing a mask) | open source | N | 4k
OD - Human (Maturity rance: baby, child, adolescent, adult) | To be generated | N | 600/class, 100 classes |  |  |  | Cifar10 + cifar100
OD - Animal |  | N | 20k |  |  |  | Cifar10 + cifar100
OD - Face (Glasses) |  | Y | 47K |  |  |  | https://github.com/cleardusk/MeGlass
OD - Face (Hat) |  | N | 28k | 50x35
OD - Face (FaceMask) | open source |  | 4k |  |  |  | https://github.com/X-zhangyang/Real-World-Masked-Face-Dataset
OD - Vehicle (Car) |  | N | 100k | 480x640
OD - Vehicle (Truck) |  | N | 21k
OD - Vehicle (Motorcycle) |  | N | 20k
OD - Vehicle (Bus) |  | N | 4k
OD - Vehicle (Van) |  | N | 6k
OD - Vehicle (Bicycle) |  | N
OD - Vehicle (27 Colors)
License Plate | open source | N | 4500 | 1920x1080 |  |  | UFPR-ALPR, Need WD for the dataset. (ECCV2018 published)Towards Human-Level License Plate Recognition. Professor Zilei Wang (AAAI-21 Accepted) Efficient License Plate Recognition via Holistic Position Attention. Professor Zilei Wang Associate Professor with the lab of Advanced Sensing and Control as the leader of Vision and Multimedia (VIM) research group, University of Science and Technology of China (USTC). | https://web.inf.ufpr.br/vri/databases/ufpr-alpr/
Face detection | open source | N | 393k | 1024x1024
Face recognition | open source | N | 3.3M | 96x112 |  |  | Do we need to have FR for different case other then security gate
[8 empty] | 2 | 1 | 1 | 1 month
可用的數據集，從中整理出可以用的
dataset combination from multiple souce
make a subset from open-image v6 | https://storage.googleapis.com/openimages/web/download.html |  |  | 600 classes | https://storage.googleapis.com/openimages/2018_04/bbox_labels_600_hierarchy_visualizer/circle.html
| cooc2014 |  |  | 250k images | http://cocodataset.org/
| Caltech Pedestrian Dataset |  |  | 350,000bounding box |  | 10 hours of 640x480 30Hz video taken from a vehicle driving
| PASCAL VOC |  |  | 20classes,11,000images
| ImageNet-detection |  |  | 200classes,400,000images
Open Image:
Table 2: Boxes.
| Train | Validation | Test | # Classes
Images | 1743042 | 41620 | 125436 | -
Boxes | 14610229 | 303980 | 937327 | 600

## R1002-Model Selection & Trainig
R1002 - Model Selection and Training
Dataset name/identifier | Model Name | Proprietary or Open Source (with reference) | Estimated Model Size before pruning | Estimated Model Size after pruning & optimization on target HW | Estimated CPU and Resource Utilization | Explanation & Comments, including assumptions | Amount of work (Human * Month): Model selection | Amount of work (Human * Month): Training | Aitronx's Internal Cost
OD - Human (Color of clothing) | EfficientDET-D2 or D3 | Open Source | D2-35.4MB,D3-52.0MB | D2-9MB,D3-15MB | < 50% CPU |  | 1 | 4 | 2
OD - Human (Holding a bag) | EfficientDET-D2 or D3 | Open Source
OD - Human (wearing a hard hat) | EfficientDET-D2 or D3 | Open Source
OD - Human (wearing a mask) | EfficientDET-D2 or D3 | Open Source
OD - Human (Maturity rance: baby, child, adolescent, adult) | EfficientDET-D2 or D3 | Open Source
OD - Animal | EfficientDET-D2 or D3 | Open Source
OD - Face (Glasses) | EfficientDET-D2 or D3 | Open Source
OD - Face (Hat) | EfficientDET-D2 or D3 | Open Source
OD - Face (FaceMask) | EfficientDET-D2 or D3 | Open Source
OD - Vehicle (Car) | EfficientDET-D2 or D3 | Open Source
OD - Vehicle (Truck) | EfficientDET-D2 or D3 | Open Source
OD - Vehicle (Motorcycle) | EfficientDET-D2 or D3 | Open Source
OD - Vehicle (Bus) | EfficientDET-D2 or D3 | Open Source
OD - Vehicle (Van) | EfficientDET-D2 or D3 | Open Source
OD - Vehicle (Bicycle) | EfficientDET-D2 or D3 | Open Source
OD - Vehicle (27 Colors) | EfficientDET-D2 or D3 | Open Source
License Plate | EfficientDET-D2 or D3
Face detection | RetinaFace |  | RetinaFace-MobileNet0.25 >1.8MB | RetinaFace-MobileNet0.25 >0.5MB
Face recognition | MobileFaceNET |  | 3.8MB | 1MB

## R1003-BackendAp Inference Model
Model Name | Y/N, if the Provider shall deliver such an application | Cost of the back-end application | Explanation & Comments, including assumptions | Amount of work (Human * Month): | Aitronx's Internal Cost
EfficientDET-D2 or D3 | Y | 2 |  |  | 2
Scale Adaptive KCF | Y | 0.5 | MOTA suggests to set at 60. |  | 0.5
MobileFaceNET | Y | 0.5 |  |  | 0.5
LPR | Y | 2 |  |  | 2
RetinaFace/Mtcnn(Face Detect) | Y | 0.5 |  |  | 0.5
5.5

## R1004-Model Proting
R1004 - Model Porting
Use Case | Sub Use Case | Target HW (CV22 & CV25) | Environments for each to be delivered (Smart City, Retail, Enterprise Security, Education) | Explanation & Comments, including assumptions | Amount of work (Human * Month): | Aitronx's Internal Cost
USE CASE #1: Motion, Object and Facial Detection & associated Tracking and Attributes | Line Crossing and Direction | CV22 |  | Need Strong Tech Support from Secoomm
| Line Crossing and Direction | CV25
| Loitering Time | CV22
| Loitering Time | CV25
| Enter & Exit Area | CV22
| Enter & Exit Area | CV25
| Intrusion Detection | CV22
| Intrusion Detection | CV25
| Crowd Detection | CV22
| Crowd Detection | CV25
| Motion Detection | CV22
| Motion Detection | CV25
| Scene Change | CV22
| Scene Change | CV25
| Object Appears or Disappears | CV22
| Object Appears or Disappears | CV25
USE CASE #2: License Plate Detection & Recognition & associated Tracking and Attributes | Character Recognition | CV22
| Character Recognition | CV25
USE CASE #3: Facial Detection & Recognition & associated Tracking | Face Match | CV22
| Face Match | CV25
| Face Mask Detection | CV22
| Face Mask Detection | CV25
| Hard Hat Detection | CV22
| Hard Hat Detection | CV25
[5 empty] | 2.5 | 1.5

## R1005-FrontendApp
R1005 - Frontend Application
Use Case | Sub Use Case | Provide API (Yes or No) | Explanation & Comments, including assumptions | Amount of work (Human * Month): | Aitronx's Internal Cost
USE CASE #1: Motion, Object and Facial Detection & associated Tracking and Attributes | Line Crossing and Direction | Y |  | 1 | 0.5
Loitering Time
Enter & Exit Area
Intrusion Detection
Crowd Detection
| Motion Detection |  | We also have these applications. | 0.5 | 0.5
| Scene Change |  |  | 0.5 | 0.25
| Object Appears or Disappears |  | only provide simple functionaly | 0.5 | 0.25
USE CASE #2: License Plate Detection & Recognition & associated Tracking and Attributes | Character Recognition |  |  | 0.5 | 0.5
USE CASE #3: Facial Detection & Recognition & associated Tracking | Face Match |  | This quotation assumes that the person is facing the camera with an angle <10 deg. | 0.5 | 0.25
Face Mask Detection
Hard Hat Detection
|  |  | sum | 3.5 | 2.25

## R1006-Post Deployment Support
R1006 - Post Deployment Support | Re-training |  |  |  | Model Upgrades
Dataset name/identifier | List cost of re-training | List amount of time required for re-training (list any associated metrics as needed) | List turnaround time | Explanation & Comments, including assumptions for Re-training | List projected cost of the next iteration generational training | List amount of time required for re-training (list any associated metrics as needed) | List turnaround time | HW | Environments for each to be delivered (Smart City, Retail, Enterprise Security, Education) | Target required model resources | Explanation & Comments, including assumptions for Re-training | Amount of work (Human * Month): | Aitronx's Internal Cost
OD - Human (Color of clothing) |  | 1 week to enhance the model performance on the PC side. If we need to retrained for quantization, that will depends on the training tools from Sercomm/Ambarella | [5 empty] | CV22
OD - Human (Holding a bag) | [7 empty] | CV22
OD - Human (wearing a hard hat) | [7 empty] | CV22
OD - Human (wearing a mask) | [7 empty] | CV22
OD - Human (Maturity rance: baby, child, adolescent, adult) | [7 empty] | CV22
OD - Animal | [7 empty] | CV22
OD - Face (Glasses) | [7 empty] | CV22
OD - Face (Hat) | [7 empty] | CV22
OD - Face (FaceMask) | [7 empty] | CV22
OD - Vehicle (Car) | [7 empty] | CV22
OD - Vehicle (Truck) | [7 empty] | CV22
OD - Vehicle (Motorcycle) | [7 empty] | CV22
OD - Vehicle (Bus) | [7 empty] | CV22
OD - Vehicle (Van) | [7 empty] | CV22
OD - Vehicle (Bicycle) | [7 empty] | CV22
OD - Vehicle (27 Colors) | [7 empty] | CV22
License Plate | [7 empty] | CV22
Face detection | [7 empty] | CV22
OD - Human (Color of clothing) | [7 empty] | CV25
OD - Human (Holding a bag) | [7 empty] | CV25
OD - Human (wearing a hard hat) | [7 empty] | CV25
OD - Human (wearing a mask) | [7 empty] | CV25
OD - Human (Maturity rance: baby, child, adolescent, adult) | [7 empty] | CV25
OD - Animal | [7 empty] | CV25
OD - Face (Glasses) | [7 empty] | CV25
OD - Face (Hat) | [7 empty] | CV25
OD - Face (FaceMask) | [7 empty] | CV25
OD - Vehicle (Car) | [7 empty] | CV25
OD - Vehicle (Truck) | [7 empty] | CV25
OD - Vehicle (Motorcycle) | [7 empty] | CV25
OD - Vehicle (Bus) | [7 empty] | CV25
OD - Vehicle (Van) | [7 empty] | CV25
OD - Vehicle (Bicycle) | [7 empty] | CV25
OD - Vehicle (27 Colors) | [7 empty] | CV25
License Plate | [7 empty] | CV25
Face detection | [7 empty] | CV25
If we want to transfer everything to WD, R1001-R1004, need to double the workload.
If Aitronx maintains the model, we will charge them a flat fee per year.
1, keep the current level: (Low)
2, Improve accuracy? (High)
3, Add new category?
4, Change to a new SOC platform, change to a new model: Mid

## R1007-Report
R1007-Reports
Functions | Amount of work (Human * Month): | Aitronx's Internal Cost
Face Detection (FD) | 1.5 | 1
Face Recognition (FR)
Motion Detection (MD)
License Plate Recognition (LPR)
Attribute Detection (AD)
Tracking

## R1008-Schedule
[WD Smart Survillance Camera] Project Schedule | [7 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com.
Aitronx-WD smart camera project
| Project Start Date | 1/27/2021 (Wednesday) |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21
| Project Lead | [6 empty] | 25 Jan 2021 | [6 empty] | 1 Feb 2021 | [6 empty] | 8 Feb 2021 | [6 empty] | 15 Feb 2021 | [6 empty] | 22 Feb 2021 | [6 empty] | 1 Mar 2021 | [6 empty] | 8 Mar 2021 | [6 empty] | 15 Mar 2021 | [6 empty] | 22 Mar 2021 | [6 empty] | 29 Mar 2021 | [6 empty] | 5 Apr 2021 | [6 empty] | 12 Apr 2021 | [6 empty] | 19 Apr 2021 | [6 empty] | 26 Apr 2021 | [6 empty] | 3 May 2021 | [6 empty] | 10 May 2021 | [6 empty] | 17 May 2021 | [6 empty] | 24 May 2021 | [6 empty] | 31 May 2021 | [6 empty] | 7 Jun 2021 | [6 empty] | 14 Jun 2021
[8 empty] | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19
WBS | TASK | LEAD | START | END | DAYS | % DONE | WORK DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | R1001-Data Prep. |  |  | - |  |  | -
1.1 | OD-Human, Vehicle, Face (Data collection) |  | Wed 1/27/21 | Sat 2/13/21 | 18 | 0% | 12 | bar: W to S
2001-01-02 | Data Pre-process |  | Sun 2/14/21 | Sun 2/28/21 | 15 | 0% | 10 | bar: S to S
2001-01-02 | Data Labeling |  | Mon 3/01/21 | Sun 3/21/21 | 21 | 0% | 15 | bar: M to S
1.2 | License Plate |  | Wed 1/27/21 | Sun 2/07/21 | 12 | 0% | 12 | bar: W to S
2001-02-01 | Data Pre-process |  | Mon 2/08/21 | Fri 2/19/21 | 12 | 0% | 10 | bar: M to F
2001-02-02 | Data Labeling |  | Sat 2/20/21 | Fri 3/05/21 | 14 | 0% | 10 | bar: S to F
1.3 | Face Recognition |  | Sat 2/20/21 | Fri 3/05/21 | 14 | 0% | 10 | bar: S to F
2 | R1002-Training |  |  | - |  |  | -
2.1 | OD-Human, Vehicle, Face |  | Tue 3/16/21 | Fri 4/09/21 | 25 | 0% | 19 | bar: T to F
2.2 | License Plate |  | Tue 3/02/21 | Fri 3/19/21 | 18 | 0% | 14 | bar: T to F
2.3 | Face Recognition |  | Tue 3/02/21 | Fri 3/19/21 | 18 | 0% | 14 | bar: T to F
2.4 | Face Detection |  | Thu 3/18/21 | Wed 3/31/21 | 14 | 0% | 10 | bar: T to W
3 | R1003-Backend App |  |  | - |  |  | -
3.1 | EfficientDET-D2 or D3 |  | Wed 3/31/21 | Fri 4/09/21 | 10 | 0% | 8 | bar: W to F
3.2 | Scale Adaptive KCF |  | Wed 3/31/21 | Fri 4/09/21 | 10 | 0% | 8 | bar: W to F
3.3 | MobileFaceNET |  | Tue 4/06/21 | Thu 4/15/21 | 10 | 0% | 8 | bar: T to T
2003-03-01 | LPR |  | Tue 4/06/21 | Thu 4/15/21 | 10 | 0% | 8 | bar: T to T
2003-03-02 | RetinaFace/Mtcnn(Face Detect) |  | Tue 4/06/21 | Thu 4/15/21 | 10 | 0% | 8 | bar: T to T
4 | R1004-Model Porting |  |  | - |  |  | -
4.1 | Model Porting on CV22 |  | Thu 4/15/21 | Wed 5/19/21 | 35 | 0% | 25 | bar: T to W
4.2 | Model Porting on CV25 |  | Thu 4/15/21 | Wed 5/19/21 | 35 | 0% | 25 | bar: T to W
5 | R1005-Frontend App |  |  | - |  |  | -
5.1 | Use Case #1 |  | Thu 5/20/21 | Wed 6/02/21 | 14 | 0% | 10 | bar: T to W
5.2 | Use Case #2 |  | Thu 5/20/21 | Wed 6/02/21 | 14 | 0% | 10 | bar: T to W
5.3 | Use Case #3 |  | Thu 5/20/21 | Wed 6/02/21 | 14 | 0% | 10 | bar: T to W
6 | R1007-Report Prep. |  |  | - |  |  | -
6.1 | Reports and Documents |  | Wed 6/02/21 | Tue 6/22/21 | 12 | 0% | 15 | bar: W to S
6.1 | Integration & full testing |  | Wed 6/02/21 | Tue 6/22/21 | 16 | 0% | 15 | bar: W to S

## R1009-Quote
R1009-Quote
Req. | Requirement Description | Cost | Explanation & Comments, including assumptions for Re-training | Amount of work (Human * Month): | Aitronx's Internal Cost
R1001 | Dataset | 8 |  | 4 | 1
R1002 | Model Selection & Training | 10 |  | 5 | 2
R1003 | Backend App. | 14 |  | 7 | 5.5
R1004 | Model Porting | 5 |  | 2.5 | 1.5
R1005 | Frontend App. | 7 |  | 3.5 | 2.25
R1006 | Post Deployment Support | 20 | This is an optional fee if WD wants pay Aitronx an anneal service fee and do the basic model maintenance. (See R1006) | 10 | 8
R1007 | Report | 3 |  | 1.5 | 1
| Sum | 67 |  | 33.5 | 21.25
|  |  |  | Fee charge for each human*month | 2